## Weekly Scrum Report
| Question | Week #1 | Week #2 | Week #3 | Week #4 | Week #5 | Week #6 | Week #7 | Week #8 | Week #9
Sarjak | What tasks did I work on / complete? | Tech Stack Selection, Requirement Analysis, Project Structure | Architectural Design | Database Design, API Defination | Revisting UML Diagram, Backend API Implementation | Backend API - 2 | Backend API -3 | API Integration- 1 | API Integration- 2 | Project Report
| What am I planning to work on next? | Architectural Design | Database Design, API Defination | Revisting UML Diagram, Backend API Implementation | Backend API - 2 | Backend API -3 | API Integration- 1 | API Integration- 2 | Project Report | -
Aman | What tasks did I work on / complete? | Tech Stack Selection, Requirement Analysis, Project Structure | Architectural Design | Database Design, Dummy Data Filling, Wireframe Design - 1 | Revisting UML Diagram, Base UI Implementation | Base UI Implementation - 2 | Base UI Implementation - 3 | UI Update - 1 | UI Update - 2 | Project Report, UI Final
| What am I planning to work on next? | Architectural Design | Database Design, Dummy Data Filling, Wireframe Design - 1 | Revisting UML Diagram, Base UI Implementation | Base UI Implementation - 2 | Base UI Implementation - 3 | UI Update - 1 | UI Update - 2 | Project Report, UI Final | -
Rajvi | What tasks did I work on / complete? | Tech Stack Selection, Requirement Analysis, Project Structure | Architectural Design | Database Design, Wireframe Design - 1, Environment Setup | Database Implementation, Revisting UML Diagram | Wireframe Design - 2, Base UI Implementation - 2 | Architectural Design - 2 | API Integration- 1 | API Integration- 2 | Project Report, Deployment
| What am I planning to work on next? | Architectural Design | Database Design, Wireframe Design - 1, Environment Setup | Database Implementation, Revisting UML Diagram | Wireframe Design - 2, Base UI Implementation - 2 | Architectural Design - 2 | API Integration- 1 | API Integration- 2 | Project Report, Deployment | -